## Project Overview
Project Overview
Field | Details
Project Name | Amazon App Testing
Application Type | Web Application
Testing Type | Manual Testing
Website | https://www.amazon.in/
Module Tested | Login,Serch Product,Add to Cart,Checkout
Testing Tyes | Functional Testing,UI Testing,Validation Testing
Tester Name | Neha Jogale
Date | 2026-03-15

## Test Scenerios
Scenrio Id | Module | Scenerio
TS01 | Login | Verify login with valid credentials
TS02 | Login | Verify login with invalid password
TS03 | Login | Verify login with empty fields
TS04 | Login | Verify Password masking
TS05 | Login | Verify Forgot password link
TS06 | Search | Verify search with valid product name
TS07 | Search | Verify search with partial product name
TS08 | Search | Verify search results display relevant products
TS09 | Search | Verify search with empty search fields
TS10 | Search | Verify search with numbers only
TS11 | Search | Verify search with special character only
TS12 | Search | Verify search with very long text input
TS13 | Cart | Verify Add product to cart
TS14 | Cart | Verify remove product from cart
TS15 | Cart | Verify update quantity in the cart
TS16 | Cart | Verify discount on the product in the cart
TS17 | Checkout | Verify checkout process
TS18 | Checkout | Verify order confirmation message after successful order
TS19 | Checkout | Verify order cannot be placed without selectng an order

## Test Cases
Test Case | Test Case | Steps | Test Data | Expected Result | Actual Result | Status
Id
TC01 | Valid Login | 1. Open website 2. Click Sign In | Username:testeruser@gmail | User should login successfully | User login successful and redirected | Pass
|  | 3. Enter valid credentials 4. Click Login | .com Password:Test@123 |  | to homepage
TC02 | Invalid Login | Enter valid username and wrong password | Username:testeruser@gmail | Error message displayed | Error message displayed | Pass
|  | Click login | .com Password:rest@123
TC03 | Login with Empty field | Click login without entering Email & | blank | Validation message should appear | “Email/Password required" | Pass
|  | Password |  |  | message displayed
TC04 | Password masking | Enter Password in password field | Password:Test@123 | password should be hidden | Password is masked with dots(…..) | pass
(dots/asteriks)
TC05 | Forgot Password | 1.Open website 2.Click 'Forgot password' | Email:testeruser@gmail.com | Reset password/OTP should be | OTP /resent link received on email | Pass
|  | 3.Enter registered email 4.Click Submit |  | sent
TC07 | Search with valid | Enter product name -> click search | Laptop | Relevant products should be | Laptop related products displayed | Pass
| product name |  |  | displayed
TC08 | Search with Partial | Enter partial keyword->click search | Lap | Related products should be | Products matching "lap" displayed | Pass
| product name |  |  | displayed
TC09 | Search results display | Search product | Mobile | Results should match searched | Mobile related products displayed | Pass
| relevant products |  |  | keywords
TC10 | Search with Numbers | Enter numbers-> search | 12345 | System should display relevant | System displayed products related | Pass
| only |  |  | products based on input | to numbers
TC11 | Search with Special | Enter Special characters -> Search | ^^%^ | Proper validation message or no | System displayed unrelated | Fail
| Characters only |  |  | result messages | products
TC12 | Search with very long | Enter long string-> Search | 200+ chracters | System should not crash | System displayed unrelated | Fail
| text input |  |  |  | results(prime video)
TC13 | Add product to cart | Select product -> Click Add to Cart | Product : Laptop | Product should added to Cart | Product added successfully to cart | Pass
TC14 | Remove product from | Remove product from cart | Product : Laptop | Product should be removed from | Product removed from the cart | Pass
| cart |  |  | cart
TC15 | Update quantity in | Change the quantity in cart | Quantity:2 | Quantity should update correctly | Quantity updated and price | Pass
| cart |  |  |  | recalculated
TC16 | Discount on product in | Add discounted product to cart | Product with discount | Discount should be reflect on total | Discount applied correctly on cart | Pass
| cart |  |  | price | total
TC17 | Checkout process | Click Checkout -> Enter details -> Place | Address,Payment details | Order should be delievered | Order placed successfully | Pass
|  | order |  | successfully
TC18 | Order confirmation | Complete order process | Valid order details | Confirmation message should be | Order confirmation message | Pass
| message |  |  | displayed | displayed
TC19 | Order cannot be placed | Go to checkout without adding product | No product | System should not allow checkout | System show message like Your | Pass
| without product |  |  |  | cart is empty

## Bug Report Sheet
Bug ID | Bug Title | Steps to reproduce | Expected Result | Actual Result | Severity | Priority
BUG01 | Search result is not loading | 1.Open the website 2.Search | Result should be displayed | Page keeps loading | High | High
any product 3.Click search
button
BUG02 | Add to cart button misaligned | 1.Open the website 2. | Button should be aligned | Button overlapping text | Low | Medium
|  | Observe the button | properly
BUG03 | Search shows irrelevant | 1.Enter special symbol in | System should show No results/ | Random products | Medium | Medium
| results for special symbol | search bar 2.Click search | Validation message | displayed
BUG04 | Search shows irrelevant | 1.Enter a long text in search | System should show relevant result | Prime video content | Medium | Medium
| results for long text | bar 2.Click seach | or no result | displayed

## Screenshots
Login Page
Product page
Add to Cart Page

## Test Summary Report
t
Test Summary Report
Project: Amazon app Testing
Total Test Cases: 19
Passed: 17
Failed: 2
Total Bugs Found: 4
| Testing Types Performed: | 0
Functional Testing
UI Testing
Validation Testing